## Wordpress
Module # | Features | Descrition | Comments | Plugin Suggestions | ETA
| About the website | Website is intended to be a more robust paywalled Instagram.restricting access to content via a paid subscription. It is essentially a network of mini paysites with recurring subscriptions | Doable
| General | Models can create a profile and have their own unique URL | Doable |  | 2 days
|  | Models can upload photos and videos, they are needing to be able to live stream Pay Per minute to their followers. and post premium videos that are an upsell to followers, but a stand alone to sell to fans online. | Doable via Woocommerce Intregration | https://wordpress.org/plugins/youtube-live-stream-auto-embed/ https://www.wpeka.com/how-to-stream-live-videos-to-your-wordpress-site.html https://restream.io/ | 5 days
|  | Fans can pay to "follow" a models profile/ feed | Doable via Woocommerce Intregration |  | 1 day
|  | Fans can message , Like, comment, Etc. | Doable |  | 2 days
|  | Admin needs to oversee all data stats payouts, messaging and much more. | Doable via Woocommerce Intregration |  | 2 days
1 | Current Core Functionality - Models | Models Via Model Portal (models.ismygirl.com) | Frontend Dashboard |  | 5 days
|  | Apply to be model fill out all vital information, upload IDs | Customized plugin will be used
|  | Create Profile, header, Avatar, Bio | Doable
|  | Post Photos, ( individual and galleries, Take photo from phone) | Will be done via Posts
|  | add captions | Will be done via Posts
|  | Send and reply to messages | Messaging plugin will be used |  | 1 day
|  | Post Videos | Will be done via Posts |  | 1 day
|  | Read and delete comments | Will be done via Posts |  | 1 day
view model admin ( follower count, Money paid, money due, etc)
2 | Current Core Functionality - Fans | Fans will have a Fan Portal | Customized plugin | Woocommerce login system | 10 days
Follow models (Pay, view content, message models)
Create Account
|  | Like, and comment on Models Photos and videos | Messaging plugin | https://wordpress.org/plugins/front-end-pm/ https://codecanyon.net/item/yobro-wordpress-multi-user-private-messaging-plugin/20563304
|  | Message Models they are following | Doable
|  | View subscriptions / follows in fan dashboard | Doable
|  | manage subsriptions Currently not working - Fans currently cannot "unfollow" they either email support@ismygirl.com (Lupe) or they email centrobill and cancel payment there and they fwd to us., Very inefficient, fans get mad they cant cancel | Doable
3 | Current Core Functionality - Admin | Admin will have a Admin Portal | Wordpress Default |  | 20 days
|  | See all Revenue, numeric and Graph | Woocommerce
Approve Models
Change models status
|  | Message Models Manual email or internal (intercom) | intercom plugin
|  | Monitor Messages ( flagged keywords) | Tags
|  | View all Customers (Users) | Userlist
|  | View all Comments | User Comments
|  | View all Transactions | Woocommerce
|  | View and manage Payouts (incomplete currently) | Woocommerce
|  | Search for Models or Users | Woocommerce
Manage FAQ ( still need to link these to the site visibly for both models and Users)
|  | Reports ( this is new and seemingly inaccurate) tied to the inaccuracies in the billin | Woocommerce
|  | View Income per period and Payouts ( also incomplete) | Woocommerce
|  | Manage Models pay % | Woocommerce | Query
4 | New Features | PPM Live Streaming |  | https://www.modenacam.com/modenacam_demo#DEMO | 3 days
|  | Test NEON App for RTMP Live Stream | Query (This is an apple app)
|  | Attatch photos or videos in direct messages to be unlocked | Query
|  | Premium Videos for sale to followers | Doable |  | 3 days
|  | Model needs to be able to send premium videos via text and have followers pay to unlock and mass send to ALL followers | Doable
|  | Model needs to be able to have her twitter say she has a new follower | Doable via Twitter API |  | 2 days
|  | Tipping Feature Fans to tip model any amount ( 80% to model) | Doable via a plugin | https://codecanyon.net/item/woocommerce-donation-or-tip-on-cart-and-checkout/11758809 For split payment we will use ---https://codecanyon.net/item/woocommerce-paypal-adaptive-split-payment/7948397 | 3 days
5 | 3rd Party Integrations | Centrobill | Via Woocommerce plugin | https://github.com/Centrobill/wc-centrobill | 6 days
|  | Epoch CC processor (approved) | Doable via a plugin, need to do more RND/ We need Mastercode on singup on epoch.
|  | Seg Pay CC processor ( approved) |  | https://www.sagepay.co.uk/partners-and-developers/ecommerce-software-package/integrate-sage-pay-with-woocommerce
|  | new approved model application needs to add email address into Fanbridge | Email marketing and newsletter | https://wordpress.org/plugins/fanbridge-signup/?utm_source=blog&utm_medium=link&utm_campaign=wordpressplugin&src=socm_blog
|  | Add Fanbridge mailing list embed | Email marketing and newsletter | Doable via fanbridge plugin
|  | INTEGRATE and Link to IMG socials | Social | Doable
|  | TWITTER INTEGRATION ala ONLY FANS | Doable via Twitter API
|  | Intercom | Doable | https://wordpress.org/plugins/intercom/
|  | New Relic | Doable | https://wordpress.org/plugins/wp-newrelic/
|  | MailGun/ Mandrill (transactional Email) | Doable | https://wordpress.org/plugins/mailgun/ https://wordpress.org/plugins/wpmandrill/
|  | Affiliate Program ( Vet Sliiing vs Nats) | We will use Nats 4 and 5 | https://wordpress.org/plugins/affiliates/ https://wordpress.org/plugins/affiliates-manager/
|  | Lively.TV (Live Streaming) | We need the API and documentation
|  | streamate popup/under/ tab | We will use a plugin, need to do more RND | https://wordpress.org/plugins/yith-woocommerce-popup/
|  | Link to and promote Streamate console www.ismygirllive.com | Please elaborate
|  | fanbridge email capture | Doable via fanbridge plugin